## Slide 1
OVPM Co-Design Toolkit · Tool 66 of 133
Method canvas for co-design
Mandate & political commitment note
What this tool produces · A formally signed charter or policy mandate that publicly commits local authorities and elected officials to support, fund, and implement the urban intervention,.
G3 · Proof of Anchoring
Dimensions
Regulation
Economic
With simplexity

## Slide 2
TOOL 66 · FACILITATOR PREPARATION
Preparing the workshop · Mandate & political commitment note
G3 · Proof of Anchoring
Why this tool matters
Forcing the administration to put its name on the line; transforming vague political promises into a binding contract that the community can use to demand accountability.
Evidence we produce
A formally signed charter or policy mandate that publicly commits local authorities and elected officials to support, fund, and implement the urban intervention,.
Duration & Material
Duration · 1 to 2 months of negotiation and drafting Material · Policy briefs, legislative review documents, formal municipal resolutions
Reference case
Within the UN-Habitat Incremental and Participatory Toolbox for Urban Planning, examining the political champions and decision-makers of the urban planning system is a mandatory first step. By securing a clear mandate and aligning the project with the broader institutional structure from week one, planning teams prevent their technical work from being discarded during future political transitions.
Suggested agenda · Brief (10 min) › Method walk-through (15 min) › Animation canvas (60–90 min) › Harvest (20 min)
With simplexity

## Slide 3
TOOL 66 · ANIMATION CANVAS · MANDATE & POLITICAL COMMITMENT NOTE
Mandate template · scope · ambition · constraints
Duration
1 to 2 months of negotiation and drafting
Project mandate
signed by the political sponsor
Project name
Sponsor (elected)
Scope (in / out)
Ambition level
Time horizon
Resources unlocked
Decisions delegated
Reporting cadence
Risks acknowledged
With simplexity

## Slide 4
TOOL 66 · HARVEST
Harvesting our learnings
After running the canvas, capture three layers of insight.
Stand-out signals, surprising stories, ideas to remember
Concrete adaptations to our context, our team, our constraints
Skills, allies, resources, decisions still to secure
What inspires me
How to apply it here
What we need to be autonomous
Each participant fills a copy. Then debrief together to surface patterns and next steps.
With simplexity